## columns&example
Contract | Car Type | car number | Station | Work Location | Day | Shift | Seq# | Mvt/Assy | Description | Assembly Time | Assigned | Breaks | Start Time | End Time
74 | B |  | 10 | CEILING | 1 | 1 | 10002 | A8620034M02 | 600V CONDUIT END 1 INSTL | 45 | B1-C1 | 0 | 7:00 | 7:22
74 | B |  | 10 | INTERIOR | 1 | 1 | 10003 | A8620034M01 | 600V CONDUIT END 2 INSTL | 45 | F1 | 0 | 7:23 | 8:08
74 | B |  | 10 | INTERIOR | 1 | 1 | 10004 | A4210055M04 | REMOVE Door OpsTBs Left & Right | 60 | A1 | 0 | 7:00 | 8:00
74 | B |  | 10 | CEILING | 1 | 1 | 10005 | A4110023M01 | HVAC DISTRIBUTION INSTL END 2 A&B CARS | 120 | A1 | 15 | 8:01 | 10:16
74 | B |  | 10 | CEILING | 1 | 1 | 10006 | A4110023M02 | HVAC DISTRIBUTION INSTL END 1 B CAR | 120 | E1 | 30 | 10:17 | 12:47
74 | B |  | 10 | CEILING | 1 | 1 | 10007 | A4110022M01 | MAIN AIR DUCT structure INSTL B CAR | 90 | B1-C1 | 0 | 12:48 | 13:18
74 | B |  | 10 | CEILING | 1 | 1 | 10008 | A5730165M03 | ROUTE C3 CEILING LHS B CAR | 236 | B1-C1 | 15 | 8:09 | 9:23
74 | B |  | 10 | CEILING | 1 | 1 | 10009 | A5730165M01 | ROUTE C2 CEILING LHS B CAR | 153 | B1 | 0 | 9:24 | 10:02
74 | B |  | 10 | CEILING | 1 | 1 | 10010 | A5730165M02 | ROUTE C1 CEILING LHS B CAR | 196 | B1 | 0 | 10:03 | 10:52
74 | B |  | 10 | CEILING | 1 | 1 | 10011 | A5730152M03 | ROUTE C3 CEILING RHS B CAR | 227 | B1 | 0 | 10:53 | 11:49
74 | B |  | 10 | CEILING | 1 | 1 | 10012 | A5730152M02 | ROUTE C2H CEILING RIGHT B CAR | 163 | B1-C1 | 30 | 11:50 | 13:00
74 | B |  | 10 | CEILING | 1 | 1 | 10013 | A5730152M01 | ROUTE C1H CEILING RIGHT B CAR | 135 | C1 | 0 | 13:01 | 13:34
74 | B |  | 10 | INTERIOR | 1 | 1 | 10014 | A4210055M05 | REPLACE Door OpsTBs Left & Right | 60 | C1 | 15 | 13:35 | 14:50
74 | B |  | 10 | STATION | 1 | 1 | 10015 | 10 1 1 CLEAN | CLEAN-UP St 10 DAY 1 | 30 | B1-C1 | 0 | 15:20 | 15:30
74 | B |  | 10 | INTERIOR | 1 | 2 | 10016 | A8210178M02 | Stanchion beam Instl B car Tighten HVAC Dist Bolts | 340 | B2-C2 | 0 | 15:30 | 16:55
74 | B |  | 10 | CEILING | 1 | 2 | 10017 | A8210178M08 | COVE BEAM INSTL B CAR Verify & Rivet | 468 | B2-C2 | 15 | 16:56 | 19:08
74 | B |  | 10 | CEILING | 1 | 2 | 10018 | A8210178M04 | no1 end ceil struct instl B car Tighten Ducts& Wires | 512 | B2 | 30 | 19:09 | 21:47
74 | B |  | 10 | CEILING | 1 | 2 | 10019 | A4110022M02 | AIR DUCT JOINING & ALIGNMENT B CAR | 60 | B2 | 15 | 21:48 | 23:03
74 | B |  | 10 | CEILING | 1 | 2 | 10020 | A8210178M03 | No 2 end ceil struct instl B car Tighten Ducts& Wires | 544 | B2 | 0 | 23:04 | 1:20
74 | B |  | 10 | CEILING | 1 | 2 | 10021 | BTQA 10021 | Inspect Ceiling Structure 30 | 0 | B2 | 0 | 1:21 | 1:21
74 | B |  | 10 | CEILING | 1 | 2 | 10022 | BTQA 10022 | Work off Ceiling Structure points 30 | 0 | B2 | 0 | 1:22 | 1:22

## description
Contract | Contract associated with the road order.
Car Type | Code for type of car
Station | which station
Work Location | work location
Day | Some road orders span multiple days
Shift | Some road orders span multiple shifts
Seq# | Unique sort identifier for road order. Does not influence order of execution
Mvt/Assy | Task identifier
Description | description
Assembly Time | Duration of task in minutes
Assigned | One or more codes for positions to execute task
Assemblers | number of people working on this
Breaks | Time allocated to break in minutes
Start Time | Time to start task
End Time | Time to complete task (includes break time)
Operation (sort string) | Single column value to order day/shift
Clock Time | Actual time?
Build Rate